## Defects
Project | Bug Id | Defect Title | Sprint Id | Dev Resource | Found By | Defect Category | Description | PBI Id | Defect Type | Found On | Fix Provided By | Assigned To | Severity | Defect Status | Environment | Owned By | Fix Provided On | Steps | Expected Result | Actual Result
TUVSUD-MEDICI - TUV-SUD |  | Unable to change the Expert standards | Mock Sprint 3.2.17 | Mahendar Bachuwar | Self | Bug | Unable to change the Expert standards | 216551 | Internal | 2025-12-10 |  | Anil Maydaypalli | Minor |  | QA |  |  | Log in as assigned Reviewer Click on review page Click Change button for assigned expert | Should be able to change Expert standards. | Unable to change Expert standards.
TUVSUD-MEDICI - TUV-SUD |  | Feedback Pages ¦ Feedback Type dropdown -> Response Accepted value is not displayed for assigned trainee | Mock Sprint 3.2.17 | Mahendar Bachuwar | Self | Bug | Feedback Pages ¦ Feedback Type dropdown -> Response Accepted value is not displayed for assigned trainee | 216551 | Internal | 2025-12-10 |  | Anil Maydaypalli | Minor |  | QA |  |  | Login to the application as an assigned trainee. Navigate to the Feedback Pages. Open any feedback record. Click on the Feedback Type dropdown. | “Response Accepted” value should be displayed in the Feedback Type dropdown for the assigned trainee. | “Response Accepted” value is not displayed in the Feedback Type dropdown.