## Defects
Project | Bug Id | Defect Title | Sprint Id | Dev Resource | Found By | Defect Category | Description | PBI Id | Defect Type | Found On | Fix Provided By | Assigned To | Severity | Defect Status | Environment | Owned By | Fix Provided On | Steps | Expected Result | Actual Result
TUVSUD-MEDICI - TUV-SUD | 1 | Inconsistent behavior when uploading files with filenames longer than 126 characters | Mock Sprint 3.2.17 | Navaneetha Narahari | Self | Bug | Inconsistent behavior when uploading files with filenames longer than 126 characters | 186880 | Internal | 30 December 2025 |  | Navaneetha Narahari | Minor |  | QA |  |  | Navigate to the Document Upload section. Upload a file with a filename longer than 126 characters – upload succeeds. Select a different document configuration and upload the same file – upload fails. | The system should handle filename length consistently across all configurations, either allowing or restricting filenames exceeding 126 characters, with clear messaging if restricted. | Uploading files with filenames longer than 126 characters succeeds in some configurations but fails in others.
TUVSUD-MEDICI - TUV-SUD | 2 | Downloaded filenames are truncated to 44 characters regardless of original filename length | Mock Sprint 3.2.17 | Navaneetha Narahari | Self | Bug | Downloaded filenames are truncated to 44 characters regardless of original filename length | 186880 | Internal | 31 December 2025 |  | Navaneetha Narahari | Minor |  | QA |  |  | Upload a file with a long filename (e.g., >126 characters). Navigate to the document download section. Download the uploaded file. Observe that the downloaded filename is truncated to 44 characters. | The downloaded file should retain the full original filename or provide a proper mechanism to handle long filenames without truncation.if it not exceeds more than 126 characters. | The downloaded filename is truncated to 44 characters, regardless of the original filename length.